## Requirements
RequirementID | Short Description | Requirement Status (Complete/Incomplete) | Developers Assigned | Developers Who Completed | Standalone/Dependent | Priority | Critical/Not Critical
1 | Course Scheduling Algorithm | Complete | Mark, Brandon | Mark | Dependant | 10 | Critical
2 | User Interface | Complete | Jon, Mohamed | Jon/Mohamed | Standalone | 9 | Critiical
2.1 | Dashboards dependant on usertype | Complete | Jon, Mohamed | Jon/Mohamed | Dependant | 9 | Critical
2.2 | Admin Dashboard: Ability to update account information | Complete | Jon, Mohamed | Jon | Dependant | 4 | Not Critical
2.3 | Admin Dashboard: Can change passwords dependent on account ID | Complete | Jon, Mohamed | Jon | Dependant | 4 | Not Critical
2.4 | Faculty Dashboard: Notification Center: For degree and schedule changes | Complete | Jon, Mohamed | Jon | Dependant | 5 | Not Critical
2.5 | Admin Dashboard: Can create all types of user accounts | Complete | Jon, Mohamed | Jon | Dependant | 6 | Critical
2.6 | Faculty Dashboard: Faculty are able to approve/deny a student's schedule | Complete | Jon & Mohamed | Jon | Dependant | 7 | Critical
3 | Database tables schema | Complete | Mark, Brandon | Mark/Brandon | Standalone | 8 | Critical
3.1 | Database: User Table -- Type (Admin¦Faculty¦Student), Username, Password | Complete | Mark, Brandon | Mark | Standalone | 8 | Critical
3.2 | Database: Courses Table -- Professor, Room#, Pre-reqs, Description | Complete | Mark, Brandon | Mark | Standalone | 8 | Critical
3.3 | Database: Saving Students Generated Schedules | Complete | Mark, Brandon | Mark | Dependant | 5 | Not Critical
3.4 | Database: Faculty and Student relationship (ie Notifications, approvals, overrides, co-op approval) | Complete | Mark, Brandon | Mark | Dependant | 7 | Critical
4 | Faculty-Student Approvals | Complete | All members |  | Dependant | 7 | Critical
5 | Storing generated courses | Complete | Mark, Brandon | Mark | Dependant | 7 | Critical
6 | Course Plan Page | Complete | Jon & Mohamed | Jon/Mohamed | Dependant | 7 | Critical
6.1 | Semester view on Course Plan: Can switch between different semesters | Complete | Jon, Mohamed | Jon | Dependant | 6 | Critical
6.2 | Add Majors and Minors: Course Plan | Complete | Jon, Mohamed | Jon | Dependant | 6 | Critical
6.3 | Course Plan: Request a Co-op | Complete | Jon, Mohamed | Jon | Dependant | 6 | Critical
6.4 | Course Plan Page: Number of credit hours selector | Complete | Jon, Mohamed | Jon/Mohamed | Dependant | 5 | Not Critical
7 | API Endpoints | Complete | Mark, Brandon | Mark/Brandon | Dependant | 7 | Critical
7.1 | User route | Complete | Mark, Brandon | Mark | Dependant | 7 | Critical
7.2 | Scheduling algorithm route | Complete | Mark, Brandon | Mark | Dependant | 7 | Critical
8 | Course Info | Complete | Mark | Mark | Standalone | 7 | Critical
9 | Login Page - Front End | Complete | Jon | Jon | Dependant | 6 | Critical
10 | All passwords must be 12 characters long, with at least 1 uppercase, 1 lowercase, 1 numeric, and 1 symbol | Complete | Mark, Brandon | Mark | Standalone | 6 | Critical
11 | Pre-req warnings: Both visually, and notifying the faculty | Incomplete | All members | N/A (not needed anymore) | Dependant | 4 | Not Critical
12 | Login Page - Back End | Complete | Mark, Brandon | Mark | Dependant | 6 | Critical
13 | Each user shall have a unique username | Complete | Mark | Mark | Standalone | 5 | Not Critical
14 | Faculty Info: Name, Email, Office Location | Incomplete | All members | N/A (didn't scrap data for) | Standalone | 5 | Not Critical
15 | CSS Styling for each page | Complete | Jon, Mohamed | Jon/Mohamed | Dependant | 4 | Not Critical

## Testing
TestID | TestDescription | Test Status (Pass/Fail) | Testers Assigned | Testers Who Completed | RequirementID | Requirement Status (Complete/Incomplete) | Developers Assigned | Developers Who Completed
1 | Tested algorithm by selecting different majors and minors and ensuring that they complete the course requirments | Pass | Mark | Mark | 1 | Complete | Mark, Brandon | Mark
2 | Test for table schema ensuring the tables including everything that we need to save | Pass | Mark | Mark | 3 | Complete | Mark, Brandon | Mark
2.1 | Ensured user tables include faculty, admin, and student account types along with storing a username and password | Pass | Mark | Mark | 3.1 | Complete | Mark, Brandon | Mark
2.2 | Ensured course includes all needed information. In this case we did not include Professor and Room # since that changes by semester and the class list we obtained did not include them. | Pass | Mark | Mark | 3.2 | Complete | Mark, Brandon | Mark
2.3 | Tested that students generated schedules can be saved | Pass | Mark | Mark | 3.3 | Complete | Mark, Brandon | Mark
2.4 | Tested that faculty has approvals notification and co-op approvals via endpoints | Pass | Mark | Mark | 3.4 | Complete | Mark, Brandon | Mark
3 | Tested that students generated schedules can be approved by faculty | Pass | Mark | Mark | 4 | Complete | Mark, Brandon | Mark
5 | Tested that generated courses can be saved in the database and retrieved later | Pass | Mark | Mark | 5 | Complete | Mark, Brandon | Mark
6 | Ensured that we have all the required API endpoints for this project | Pass | Mark | Mark | 7 | Complete | Mark, Brandon | Mark
7 | Tested that we have all the required API endpoints for the basic user. IE make sure that login works. | Pass | Mark | Mark | 7.1 | Complete | Mark, Brandon | Mark
7.1 | Tested that there is a API Endpoint for scheduling | Pass | Mark | Mark | 7.2 | Complete | Mark, Brandon | Mark
8 | Ensured course info with the required course information ie pre-reqs/co-reqs/course description/course name | Pass | Mark | Mark | 8 | Complete | Mark, Brandon | Mark
10 | Tested with a unit test test to ensure password requriments are met for user creation | Pass | Mark | Mark | 10 | Complete | Mark, Brandon | Mark
11 | Ensure all necessary endpoint are up for login page and tested that logging in returns the users account type | Pass | Mark | Mark | 12 | Complete | Mark, Brandon | Mark
12 | Tested that all users must have a unique username by testing trying to create a duplicate username | Pass | Mark | Mark | 13 | Complete | Mark, Brandon | Mark
13 | Tested the frontend connections / User interface | Pass | Jon | Jon | 2 | Complete | Jon, Mohamed | Jon, Mohamed
13.1 | Tested to make sure that dashboard are only accessable by the proper user type | Pass | Jon | Jon | 2.1 | Complete | Jon, Mohamed | Jon, Mohamed
13.1.1 | Tested to make sure the student accounts are able to access the student dasboard and have it populate it with only that student's information | Pass | Jon | Jon | 2.1 | Complete | Jon, Mohamed | Jon, Mohamed
13.1.2 | Tested to make sure that faculty accounts are able to access the faculty dasboard and be able to view assigned student's schedules | Pass | Jon | Jon | 2.1 | Complete | Jon, Mohamed | Jon
13.1.3 | Tested to make sure that administrator accounts are able to access the admin dashboard | Pass | Jon | Jon | 2.1 | Complete | Jon, Mohamed | Jon
13.2 | Tested admin dashboard to make sure the administrator accounts are able to update user account information | Pass | Jon | Jon | 2.2 | Complete | Jon, Mohamed | Jon
13.2.1 | Tested admin dashboard to make sure that administrator accounts are able to change account passwords dependant on account ID | Pass | Jon | Jon | 2.3 | Complete | Jon, Mohamed | Jon
13.3 | Tested to make sure that administrator accounts are able to create new acocunts of all types | Pass | Jon | Jon | 2.5 | Complete | Jon, Mohamed | Jon
13.4 | Tested to make sure the faculty accounts are able to approve/deny schedules from their assigned students through the faculty dashboard | Pass | Jon | Jon | 2.6 | Complete | Jon, Mohamed | Jon
13.5 | Tested the course plan section of both the student dashboard and the faculty dashboard | Pass | Jon | Jon | 6 | Complete | Jon, Mohamed | Jon
13.5.1 | Tested to make sure the generated course plan was able to populate in the course plan section of the dashboards for both approved and pending schedules | Pass | Jon | Jon | 6 | Complete | Jon, Mohamed | Jon
13.5.2 | Tested to make sure that the course plan was able to switch semesters and display the corrosponding courses associated with that semester | Pass | Jon | Jon | 6.1 | Complete | Jon, Mohamed | Jon
13.5.3 | Tested to make sure that students are able to select one or more Major(s) and Minor(s) | Pass | Jon | Jon | 6.2 | Complete | Jon, Mohamed | Jon
13.5.4 | Tested to make sure that students are able to pick a semester if they would like to take a co-op | Pass | Jon | Jon | 6.3 | Complete | Jon, Mohamed | Jon
13.5.5 | Tested to make sure that the students are able to enter a total amount of credits per semester and that this is used to generate the course schedule | Pass | Jon | Jon | 6.4 | Complete | Jon, Mohamed | Jon
13.6 | Tested to make sure that the login page takes a username and password to sigin in to the different dashboards | Pass | Jon | Jon | 9 | Complete | Jon | Jon